WORLD VISION

People and Culture Department

jobs_wvbih@wvi.org

APPLICATION FOR RESEARCH

NEEDS, CHALLENGES AND COPING STRATEGIES OF CHILDREN WITH DISABILITIES (CWDS) IN BIH AND THEIR FAMILIES

Applicant: Foundation Wings of Hope

PROJECT BACKGROUND

World Vision published a Terms of Reference for the Research on needs, daily challenges and coping strategies of CWDs in BiH and their families, as well as how the government, public institutions and its policy framework contribute to CWDs status in BiH. The main purpose of this Research is to contribute to improving the system of protection of CWDs and their families as appropriate. The research will serve to all relevant stakeholders in order to provide more inclusive and supportive environment for CWDs and their families in BiH.

World Vision acknowledges that in Bosnia and Herzegovina, children with disabilities are one of the most marginalized and excluded groups in society. Facing daily discrimination in the form of damaging stigmas and a lack of adequate policies and legislation, they are effectively barred from exercising their right to healthcare, education, and even survival. They are often likely to be among the most vulnerable and poorest members of the population. They are less likely to attend school, access medical services, or have their voices heard in society. Their disabilities also place them at a higher risk of physical abuse. In Bosnia and Herzegovina, there are limited statistics and information regarding CWDs, which complicates any efforts to plan aid or provide assistance to these children and their families. This has contributed to a lack of coordination between most attempted interventions for CWDs.

In BiH, information about children with disabilities is scarce. There are several institutions that have developed frameworks regarding the sustainable collection of data on children with disabilities, however those frameworks are often not being utilized or the data being collected is beyond the comprehension of decision makers. Currently, statistical agencies in BiH are collecting statistical data on CWDs within the education sector. The Ministry of Human Rights and Refugees BiH has developed a methodological framework for the collection of data on marginalized groups of children using data from the Education, Health, Justice, Employment, Social Work and Civil Society sectors. In 2012, the Ministry of Human Rights and Refugees BiH collected information on marginalized groups of children. Information is aggregated from different sectors, however the data is not widely available to users. Administrative data in the health, education, and social work sectors about CWDs exists, but are not available to the public. In general, different sectors throughout BiH possess quantitative data on CWDs, but most of this data is not easily accessible by the general public.

In 2013, UNICEF conducted a “Knowledge, Attitudes and Practice” (KAP) study in order to assess the situation of CWDs in BiH. This study concluded that citizens in BiH are generally aware of the neglect, marginalization and lack of respect for the fundamental rights of children with developmental disabilities along with the lack of social assistance and support availiable for these children. Nevertheless, many BiH citizens have demonstrated certain stereotypical preconceptions and prejudice towards developmentally disabled children, which highlights the need to raise public awareness on the issue.

Additional information is available through reports developed by NGOs, such as DUGA and the Open Society Fund. Additionally, a number of associations are currently providing services to children with certain disabilities (Down syndrome, paralysis, hearing difficulties, etc.).

In the last five years, policy change targeting CWDs have been focused on early childhood interventions, inclusive education, placement of CWD in institutions, social protection and health protection. Most reports indicate that these policy reforms promote a number of models for good practice, however, implementation has been insufficient or incomplete, thus creating new living circumstances that could hinder the well being of CWDs in BiH.

RESEARCH FRAMEWORK

The objective of the Research Framework is to create a research design that is sensitive to the collection of data on CWDs in BiH, as well as informative to key stakeholder groups. Each research phase, as presented in the Action Plan, collects information, and then analyzes and shares the collected data with relevant stakeholders for further analysis. This way, key stakeholders can influence the created methodology design and indicator matrix.

The Research Framework proposes that the data on CWD should be collected from available administrative and statistical sources in health, education and social work sector, while information regarding the knowledge, attitudes, and practices related to CWDs should be collected from parents, children, teachers, health practitioners, social work practitioners, policy makers and decision makers. A full list of relevant stakeholders will be developed as part of the methodological design.

Project theory of change

Outcomes of the project are intended to increase evidence based programmability of measures and approaches relevant to CWDs in BiH –

PROJECT IMPACT. - Project impact will be achieved through two outcomes:

OUTCOME 1 - Increased accessibility and functionality of data on CWDs in BiH for the years of 2008 through 2015, that is available through numerous Reports and administrative data in public and civil society sector

OUTCOME 2 – Available needed information about needs, challenges and coping strategies of children with disabilities and their families in BiH

Evidence Based Programmability

Project Impact

Accesibility and functionality of data

Outcome I

Identified available information and knowledge gaps

Output 1

Policy and decision makers involved

Output 2

Availability of new data

Outcome II

Methodology developed

Output 3

New data collected

Output 4

Figure 1 Research Framework Theory of Change

Target groups

Primary beneficiary groups are CWDs and their families, while the primary target groups for the Research will include all organizations and individuals carrying information about CWDs and their families. These target groups could include; children, CWDs, parents, parents of CWDs, representatives of schools, municipalities departments, health institutions, social work institutions, and civil society organizations.

Desk Analysis will be conducted on the available literature throughout BiH.

The current proposal includes an in depth analysis of CWDs needs in education, health, social work and civil society sectors.

Targeted Areas: Republika Srpska and two Cantons (as agreed upon with World Vision).

Research Activities

Output 1. Identified available information and knowledge gaps about attitudes and practices with children with disability in BiH both at community and national level

A1.1 Mapping and acquiring available resources on situational analysis of children with disability in BiH

Available resources will be collected in communication with main organizations advocating for advancement of well-being of CWDs in BiH such as: UNICEF, Save the Children, World Vision, DUGA, Open Society Fund, Relevant Ministries (Education, Health, Social Protection, Human Rights etc.), Institution of Ombudsmen BiH, and Ombudsmen for Children RS etc. Each institution will be contacted and information about their programs and publications from 2008 till 2015 will be  collected. Each institution will also be asked for any other known source of information that could also be utilized for the project. Any available Strategy and/or Action Plan will also be inquired about.

A1.2 Conducting desk analysis

Desk analysis will provide actual data across multiple sources, make comparisons, provide information on how data are being used (if any), their importance, knowledge gaps etc., and serve as a basis for the development of the indicator matrix.

A1.3 Developing indicator matrix for desk analysis of available literature on children with disability in BiH

Based on the available resources, an indicator matrix will be developed. The Indicator matrix will summarize information given in the report. The summary will specify data in terms of description, form of data (quantitative and/or qualitative), data scale, the source Report, known validity and reliability, disaggregation by type of disability, gender, age, ethnicity/minority. A template indicator matrix sheet will be confirmed with World Vision staff prior analysis.

A1.4 Preparing preliminary report on desk analysis

Preliminary report Concept will be developed after the indicator Matrix and the preliminary Desk Analysis report are finalized.

A1.5 Discussing preliminary report findings with WV staff

Both the preliminary Report Concept and the Preliminary report will be shared with WV staff in order to ensure the relevance of data and report structure. This Preliminary Research Report will enable WV staff to provide quality feedback on the Report content.

A1.6 Finalizing Desk Research findings Report

Based on the comments from WV, a staff Final report will be produced.

Output 2. Policy and decision makers at entity/canton level informed about WV programming on children with disability and results of the Desk Research – additional information collected

A2.1 Identifying relevant entity/cantonal stakeholders

In order to design an appropriate methodology for data collection, it is important to capture the usability of existing data currently available to policy and decision makers, their view on information gaps, how information feeds policy development, and their view on what approach should be taken in collection of new data on CWDs.

A2.2 Organizing meetings with identified stakeholders, presenting research findings, collecting additional information and identifying knowledge gaps

Prior to finalizing the research methodology, meetings with key stakeholders from the Ministries and organizations producing reports on CWDs will be conducted. The main objective of the meetings will be to assess their view on needed data, methodological designs, and how the currently available data impacts policymaking. An additional objective of these meetings will be to inform stakeholders on World Vision’s programming in respect to CWDs, and obtaining approvals from ministries if required.

Output 3. Developed and agreed methodology for collection of data on children with disability and their families in BiH

A3.1 Field Research indicator matrix developed and agreed with WV

Based on the information collected, the indicator matrix for field research will be designed with these proposed research methods. The indicator matrix will emphasize if data will be comparable with data from analyzed Reports.

A3.2 Research design proposed and agreed for each indicator

After confirming indicator matrix with WV staff, each indicator will be suited in questionnaires and guidelines for collection of data.

Output 4. Field data collected from all identified stakeholders

A4.1 Interviews with expert stakeholders

Expert stakeholders will provide information about practices being employed to serve CWDs and their families. They will be asked to describe implementing services, along with their effectiveness and efficiency. Expert stakeholders will be practitioners in NGOs, social workers from Centres for Social Work, Pediatricians from Health Centres, Special educators from Agencies working with CWDs, University teachers, etc. Interviews with expert stakeholders (lasting around. 90 minutes) will be conducted. Important expert stakeholders will be identified during the desk research and meetings with the policy and decision makers.

Eight interviews will be conducted at minimum at each target location (two interviews per sector).

A4.2 Focus groups

In each target location six focus groups will be implemented.

I focus group - with entire school class,

II focus group - selected CWDs and children without disabilities

III focus group - with parents of CWD and practitioners from health sector

IV focus group - with parents of CWD and practitioners from education sector

V focus group - with parents of CWD and practitioners from social work sector

VI focus group - with parents of CWD and practitioners from civil society sector

Number of participants to each focus group will be limited to 12. Participants will come from different backgrounds: service providers, decision makers, policy makers, parents, university professors etc.

A4.3 Analyzing gaps in data knowledge

Based on the information provided through interviews and focus groups, lists of information needed by research participants will be created to gauge the need for additional information (quantitative and/or qualitative). Such information will be recorded and used for development of questionnaires for usage with a wider audience.

A4.4 Developing questionnaires for wider audience

Questionnaires will be developed for different groups and targeted locations, and then submitted to relevant authorities to complete. Relevant authorities may be Ministries, Institutions, Schools, Research Centers, Universities, Associations of parents of CWDs etc.

A4.5 Submission and collecting information with questionnaires

Created questionnaires will be submitted to identified stakeholders and follow up phone calls will ensure a response rate of at least 60%.

A4.6 Preliminary Report

Preliminary Report findings will be developed for each targeted location and in general

A4.7 Discussion on Preliminary Reports with WV staff

Preliminary Report will be submitted to WV staff for commenting

A4.8 Final Report

The Final Report will be completed in accordance with received comments on Preliminary Report.

Expectations behind Research Theory of Change

It is expected that using mixed policy and community level involvement in the methodology design and data collection process, the research will contribute to:

- increased understanding within the community about the needs of CWDs and why it is important to address these needs.

- opportunity to share how the needs of CWDs impact the quality of life for the larger community.

- increased community engagement because members from different parts of the community are included in discussions about needs, assets, and the community’s response.

- identification of a community’s strengths and weaknesses.

- mapping of resources currently available within the community that can be leveraged to improve the quality of life for CWDs.

- identification of asset gaps that exist in these communities.

- increased awareness of how individuals can contribute to CWDs well-being.

- assessing service delivery priorities.

- providing data for making decisions about the actions that can be taken to address the needs of  CWDs and how to use the available assets.

- generation of data that can be used to inform strategic planning, priority setting, program outcomes, and program improvements.

ACTION PLAN

First month: 1st of September 2015

|  | Research month |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | I | II | III | IV | V | VI | VII | VIII | IX |
| Output 1. Identified available information and gaps in knowledge about attitudes and practices with children with disability in BiH both at community and national level |  |  |  |  |  |  |  |  |  |
| A1.1 Mapping and acquiring available resources on situational analysis of children with disability in BiH | X |  |  |  |  |  |  |  |  |
| A1.2 Conducting desk analysis | X |  |  |  |  |  |  |  |  |
| A1.3 Developing indicator matrix for desk analysis of available literature on children with disability in BiH | X |  |  |  |  |  |  |  |  |
| A1.4 Preparing preliminary report on desk analysis | X |  |  |  |  |  |  |  |  |
| A1.5 Discussing preliminary report findings with WV staff | X |  |  |  |  |  |  |  |  |
| A1.6 Finalising desk research findings Report | X |  |  |  |  |  |  |  |  |
| Output 2. Policy and decision makers at entity/canton level informed about WV programing on children with disability and results of the Desk Research – additional information collected |  |  |  |  |  |  |  |  |  |
| A2.1 Identifying relevant entity/cantonal stakeholders |  | X |  |  |  |  |  |  |  |
| A2.2 Organizing meetings with identified stakeholders, presenting research findings and collecting additional information and recognizing gaps in knowledge |  | X |  |  |  |  |  |  |  |
| Output 3. Developed and agreed methodology for collection of data on children with disability and their families in BiH |  |  |  |  |  |  |  |  |  |
| A3.1 Field Research indicator matrix developed and agreed with WV |  |  | X |  |  |  |  |  |  |
| A3.2 Research design proposed and agreed for each indicator |  |  | X |  |  |  |  |  |  |
| Output 4. Field data collected from all identified stakeholders |  |  |  |  |  |  |  |  |  |
| A4.1 Interviews with expert stakeholders |  |  |  | X | X |  |  |  |  |
| A4.2 Focus groups |  |  |  |  | X | X |  |  |  |
| A4.3 Analysing gap in data knowledge |  |  |  |  |  |  | X |  |  |
| A4.4 Developing questionnaires for wider audience |  |  |  |  |  |  | X |  |  |
| A4.5 Submission and collecting information with questionnaires |  |  |  |  |  |  |  | X |  |
| A4.6 Preliminary Report |  |  |  |  |  |  |  |  | X |
| A4.7 Discussion on Preliminary Reports with WV staff |  |  |  |  |  |  |  |  | X |
| A4.8 Final Report |  |  |  |  |  |  |  |  | X |